## Sheet1
Bug Report (https://db.bpwork.xyz/)
Bud ID | Description/Summary | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority
Bug_001 | "লগ ইন" feature is not working | 1. open the website URL 2. click on "লগ ইন" from the navbar | When we click on "লগ ইন" it should redirect to login page where people need to fill the form with their login credentials | Clicking on "লগ ইন" doesn't redirect to anywhere | Critical | P0 (High)
Bug_002 | Search bar function does not work | 1. open the website URL 2. write something on search bar 3. press enter | Users should get their desired results by searching | Search bar doesn't display any search result | Major | P0 (High)
Bug_003 | Under "জেলা" menu, the informations regarding "চট্টগ্রাম" and "রাজশাহী" are missing | 1. open the website URL 2. click on "জেলা" dropdown from navbar 3. hover over "চট্টগ্রাম" or "রাজশাহী" option 4. click on "জেলা-১" or "জেলা-২" or "জেলা-৩" from multi-level dropdowns | Informations about "চট্টগ্রাম" and "রাজশাহী" should be shown when we click on multi-level dropdowns | Anything we click on under "জেলা" dropdown menu it always shows informations about "ঢাকা" divsion | Major | P0 (High)
Bug_004 | Multi-level dropdowns of "ঢাকা" have no functionality | 1. open the website URL 2. click on "জেলা" dropdown from navbar 3. hover over "ঢাকা" option 4. click on "জেলা-১" or "জেলা-২" or "জেলা-৩" from side menu | "জেলা-১" and "জেলা-২" and "জেলা-৩" should have different contents inside them | "জেলা-১" and "জেলা-২" and "জেলা-৩" take us to the same page | Major | P1 (Medium)
Bug_005 | "দর্শনীয় স্থান", "দৃষ্টিনন্দন স্থাপনা", "ঐতিহাসিক স্থান", "হোটেল-রিসোর্ট", "ঐতিহ্যবাহী খাবার"; all the buttons under the "ঢাকা" district page are redirecting to a same page-sthapona(স্থাপনা) instead of showing places according to the category | 1. open the website URL 2. click on "জেলা" dropdown menu 3. hover over "ঢাকা" option 4. click on "জেলা-১" or "জেলা-২" or "জেলা-৩" from side menu 5. In the "ঢাকা" page click on "দর্শনীয় স্থান" or "দৃষ্টিনন্দন স্থাপনা" or "ঐতিহাসিক স্থান" or "হোটেল-রিসোর্ট" or "ঐতিহ্যবাহী খাবার" | Users should be able to see related informations clicking those buttons | Users are redirected to a page-sthapona(স্থাপনা) by clicking any of those buttons | Major | P1 (Medium)
Bug_006 | The "আরও পড়ুন" button under "আহসান মঞ্জিল" or "বলধা গার্ডেন" redirects to "লালবাগের কেল্লা" | 1. open the website URL 2. go to the hompage and scroll down 3. click on "আরও পড়ুন" button under "আহসান মঞ্জিল" or "বলধা গার্ডেন" on homepage | Users are supossed to get details about "আহসান মঞ্জিল" or "বলধা গার্ডেন" accordingly | Users are being redirected to "লালবাগের কেল্লা" instead of other places that users chose | Major | P0 (High)
Bug_007 | New comment can not be posted | 1. open the website URL 2. go to the hompage and scroll down 3. click on "আরও পড়ুন" button under "লালবাগের কেল্লা" 4. write something in the comment box 5. click on post | Users should be able to post new comments using the comment box | Users can write anything on the comment box but cannot post the comment | Major | P1 (Medium)
Bug_008 | In "লালবাগের কেল্লা" page the "আরও কিছু দর্শনীয় স্থান" bar is showing the same places from previous page and hompage | 1. open the website URL 2. go to the hompage and scroll down 3. click on "আরও পড়ুন" button under "লালবাগের কেল্লা" | Users should be provided with the informations about other tourist spots | Users are getting the details about the same tourist spots they were provided in the previous page or in the hompage | Minor | P2 (low)
Bug_009 | Under "আরও কিছু দর্শনীয় স্থান" section, the "বিস্তারিত পড়ুন" buttons don't work | 1. open the website URL 2. go to the hompage and scroll down 3. click on "আরও পড়ুন" button under "লালবাগের কেল্লা" 4. click on the "বিস্তারিত পড়ুন" buttons under the section "আরও কিছু দর্শনীয় স্থান" | Users should be taken to the different page that contains detaisl by clicking "বিস্তারিত পড়ুন" button | Users are not being redirected to anywhere | Minor | P2 (low)
Bug_010 | The "আরও পড়ুন" button under "বলধা গার্ডেন" doest work in the "ফিচার" page | 1. open the website URL 2. go to the "ফিচার" page and scroll down 3. click on "আরও পড়ুন" button under "বলধা গার্ডেন" | Users should get the details about "বলধা গার্ডেন" and surroundings | Users are not being redirected to anywhere | Minor | P2 (low)
Bug_011 | The picture used for the "বলধা গার্ডেন" is irrelavant | 1. open the website URL 2. go to the hompage and scroll down | Users should see a picture related to "বলধা গার্ডেন" | Users are seeing irrelavant picture | Minor | P2 (low)
Bug_012 | The "হোটেল-রিসোর্ট" button on the navbar doesn't show any details about different hotels and resort from different divisions | 1. open the website URL 2. click on "হোটেল-রিসোর্ট" on navbar | User should get to know about hotel booking and other details in this page | Users are getting the same details they got by clicking "জেলা" on navbar | Major | P0 (High)
Bug_013 | The "শেয়ার" button on the "ভ্রমন অভিজ্ঞতা" page doesn't work | 1. open the website URL 2. click on "ভ্রমন অভিজ্ঞতা" on navbar 3. write something on "শিরোনাম" and "বর্ণনা" 4. upload a photo clicking on "Choose file" 5. click on "শেয়ার" button | Users should be able to upload their travel experince with photo | "শেয়ার" button doesn't post whatever users write in "ভ্রমন অভিজ্ঞতা" form | Major | P0 (High)
Bug_014 | In the "জানতে চাই" page, form submission doesn't work | 1. open the website URL 2. click on "জানতে চাই" 3. fill in the fields given in the form 4. click on "সাবমিট" button | "জানতে চাই" page's form should be submitted | Form does not submit any information | Major | P1 (Medium)
Bug_015 | The "ফিচার" in navbar is providing the same informations users get on hompage and so this functionality is irrelavant | 1. open the website URL 2. click on "ফিচার" | Users should get some informations or functionality different from hompage | They are getting same informations as hompage | Major | P2 (low)
Bug_016 | The "ভ্রমন ইভেন্ট" button in navbar is providing the same informations as users get on hompage | 1. open the website URL 2. click on "ভ্রমন ইভেন্ট" | Users should get travel events and their details under this section | They are getting same informations as hompage | Major | P0 (High)
Bug_017 | Profile page shows static user profile | 1. open the website URL 2. click on the profile menu from the navbar | Users should get to see their profile details | All the users can see the same profile of "নাদিম মজিদ" | Major | P0 (High)
Bug_018 | Profile can not be edited | 1. open the website URL 2. click on the profile menu from the navbar 3. click on edit button 4. change any info 5. submit the form | Users are supposed to see the updated info that they entered in the edit profile form | Edit profile submit button doesn't respond | Major | P0 (High)
Bug_019 | Edit and delete buttons under "ভ্রমন অভিজ্ঞতা" and "কমেন্ট" tabs on profile doesn't work | 1. open the website URL 2. click on the profile menu from the navbar 3.click on "ভ্রমন অভিজ্ঞতা" or "কমেন্ট" tabs 3. click on edit or delete button | users should be able to edit or delete things | if we click on edit or delete button nothing changes | Minor | P1 (Medium)
Bug_020 | Social media buttons in the footer are irresponsive | 1. open the website URL 2. scroll down to the footer | Social media links in the footer should take users to different pages accordingly | Socila media links in the footer don't respond on click | Minor | P2 (low)
Bug_022 | Carousel's images aspect ratio is not maintained in the homepage | 1. open the website URL | Images aspect ratio should be mainted so that they look good | Images widths are more compared to heights which makes landing page less attractive | Minor | P2 (low)
Bug_023 | On hovering over navbar menus, they become unclear due to background color | 1. open the website URL 2. hover over any navbar menu | Navbar menu should be different color than the background on hover over | Navbar menu become of the same color as the background on hover over | Minor | P2 (low)